## 3월 업무추진일정표 (hidden)
단기-업무추진일정표
구분 | 항목 (진행중-주황색 / 완료-회색) | 담당 | 위원회 | 2 |  |  | 2월 | [7 empty] | 3 |  |  | 3월 | [30 empty] | 4 |  |  | 5 |  |  |  |  | 6 (마지막주 월요일은 7월에 포함) |  |  |  | 7 |  |  |  |  | 8 | [30 empty] | 9 | [29 empty] | 10 |  |  |  |  | 11
사후
|  |  |  | 상 | 중 | 하 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 상 | 중 | 하 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 상 | 중 | 하 | 1주 | 2주 | 3주 | 4주 | 5주 | 1주 | 2주 | 3주 | 4주 | 1주 | 2주 | 3주 | 4주 | 5주 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 D-Day | 30 2일차 | 1 3일차 | 2 4일차 | 2주 | 3주 | 5주 | 1주 | 2주
기획/ 재무 | 전체 수입 및 지출 예산 관리 | 공동 | 회장단
| PCO 계약 | 공동 | 회장단
| 제주컨벤션뷰로 지원금 업무(2천만원 승인됨) | PCO | 운영,재무
| 호텔 선정 및 블록 | PCO
| 제주ICC 홈페이지 일정 게재 요청(국,영문) | PCO | 학술
| 심포지아, 후원 섭외 및 관리 | 학회 | 학술
| 전시광고부스 후원금 유치 및 관리 | 학회 | 운영, 기획, 재무
| 운영계획안 | PCO
| 시나리오 | PCO
| 행사장 최종 점검 및 현장 운영 | 공동
| Thanks Letter | PCO | 학술
| 결과보고/강연자료/사진 제출 | PCO
| 제주컨벤션뷰로 결과보고 | PCO | 운영, 기획, 재무
운영 | 행사장 답사 및 대관 담당자 미팅 | PCO | [13 empty] | 1차 | [12 empty] | 답사 |  |  |  |  | 보고서 | [26 empty] | 2차 | [35 empty] | 최종
| 행사장 배치도 작성 및 전달 | PCO
| 각 위치별 기자재 및 물품 준비 및 점검 | PCO
| 진행요원 채용 및 교육 / 관리 | PCO
| 체크리스트 작성 및 점검 | PCO | [108 empty] | 1차 | [9 empty] | 2차
| 기자재 설치 및 운영요원 배치 | PCO
학술 | 행사 주제 및 토픽 선정 | 학회 | 학술
| 연자 초청 및 확정 (PL/Symposia) | 공동 | 학술 |  |  | 초청 | [8 empty] | 35/125 | 40/125 | 접수마감 3.28 89/125 | [17 empty] | 42 | [6 empty] | 50 |  |  | 마감
| Abstract 접수 | PCO | 학술 | [89 empty] | 마감
| 발표자 강연자료 접수/마감 | PCO | 학술 | [89 empty] | 마감
| 발표자 & 학술 프로그램 계획 및 확정 | 공동 | 학술 | [89 empty] | 포스터
| 연자용 PPT 템플릿 업로드 | PCO
| 좌장 확정 및 배정 | 학회 | 학술
| 좌장: 발표자 초록, cv, 좌장가이드 전달 | PCO | 학술 | [89 empty] | 1차 | [24 empty] | 2차 | [6 empty] | 현장
| 연자: 연자 가이드 | PCO | 학술 | [89 empty] | 1차 | [24 empty] | 2차
| Hanmi TGA 초청 및 심사, 폐회식 참여 안내(국제협력) | PCO | 국제협력 | [49 empty] | 의뢰 | [38 empty] | 확 정 | 초록 수령 | [10 empty] | R.M
| 연자 선정 및 안내-일천 | 학회 | 기획 | [49 empty] | 의뢰 | [11 empty] | 확정 | [26 empty] | 확 정 | 초록 수령 | [10 empty] | R.M
| 상패 제작 및 검토 | PCO | 학술상 | [90 empty] | 제 작 |  |  | 검 토
| KSMCB TGA 마감, 심사, 폐회식 참여 안내 | PCO | 학술 | [100 empty] | R.M
| YI 마감, 심사, 초록집 수록, 폐회식 참여 안내 | PCO | 학술 | [100 empty] | R.M
| 일자별 포스터 카테고리 배분 | PCO | 교육
| 우수포스터상 평가위원 일자별 카테고리별 필요인원 결정 | PCO | 교육
| 평가위원 관리를 위한 구글폼 제작 | PCO | 교육
| 우수포스터상 평가위원 선정 | PCO | 교육
| 우수포스터상 평가위원 섭외 메일(배정포스터) 발송 | PCO | 교육
| 심사표 구글폼 및 심사용지 인쇄하여 준비 | PCO | 교육
| 우수포스터 신청 포스터 학회로고 스티커 부착 | PCO
| 평가위원 명찰 수령 및 서명 취합 | PCO
| 우수포스터상 심사용지 배부, 취합 후 점수표 계산 | PCO | 교육
| 최종 우수포스터상 수상자, 대표 수상자 선정 | PCO | 학술
| 선정 수상자 안내 문자 및 메일 발송(TGA,YI구별) | PCO | 학술
| 폐회식 슬라이드 우수포스터상 수상자 성함 기재 | PCO
| 우수포스터상 상장 현장 출력 | PCO
| 폐회식 후 상장 전달 | PCO
| 발표자,좌장 참석확인 및 현장운영 | PCO | 학술
| 우수포스터 상장 미수령자 우편발송 | PCO
| 우수포스터상 수상자 계좌 및 개인정보 취합 후 전달 | PCO
| 의협 연수평점 결과보고 | PCO | [83 empty] | 신청
홍보 | 홍보대상기관 및 대상자 리스트업 | 학회 | 학술
| 홍보대상기관 및 대상에 발송 | PCO | 학술
| ICKSMCB 홈페이지 오픈 | 학회 | 학술 | [52 empty] | 오픈
| ICKSMCB 홈페이지 관리 | PCO | 학술
| 웹용 Newsletter | 공동 | 학술
| 포스터 제작 및 발송(이메일/우편) | PCO | 학술
| 행사홍보 동영상 | PCO | 학술
| 개회식 / 시상식 식순영상 | PCO | 학술
| 현장거치 제작물 | PCO | 학술
| 행사장 제작물 시공 및 세팅 | PCO
| 현장 사진 촬영/편집 | PCO
| 홈페이지 사진 거재 | 공동 | 전산
| ICKSMCB 2026 키비쥬얼 제작 | PCO | 회장단
후원/ 전시 | 후원/전시업체 리스트업 및 섭외 | 학회 | 기획
| 후원/전시 접수 | 학회 | 기획
| 후원/전시비 확인 및 관리 | 학회 | 기획
| 후원사(전시업체) 광고 및 로고 접수 | PCO | 기획
| 전시안내문 제작 및 배포 | 학회 | 기획
| 전시장 배치도 전달 | PCO | 기획
| 전시부스 위치 선정 | 학회 | 기획
| 전시업체 부스위치 전달 | PCO | 기획
| 전시업체 현장 가이드 전달 | PCO | 기획
| 전시장 세팅 및 현장운영 | PCO | 기획
등록 | 사전등록 접수 및 리스트업 | PCO | 학술
| 등록비 관리 및 확인서(메일,문자) 발송 | PCO | 학술
| 등록물품(명찰KIT) 확정 및 준비 | PCO | 회장단
| 등록처 기자재 설치 | PCO
| 등록요원 배치, 현장 운영 | PCO
| 참가자 리스트, 등록결과 보고(매일) | PCO | 학술
숙박&교통 | 온라인 예약 오픈 및 관리 | PCO | 학술
| 초청연사 호텔예약 확인 및 안내 | PCO | 학술
| 최종 블록 정리 | PCO
| 현장 객실 체크인&아웃 확인 | PCO
| VIP 교통편 예약 및 관리 | PCO
| 공항 안내데스크 운영 | PCO
공식/ 사교행사 | 공식/사교 행사장 선정 |  | 회장단
| 연회 스타일별 메뉴결정 |  | 회장단
| 행사별 식순 및 연설자 선정 |  | 회장단
| 연설문 초안 작성 |  | 회장단
| 개회식(or 만찬) 공연 |  | 회장단
| 식수인원 최종통보(2~3주전) |  | 회장단
| 행사장 배치도면 및 시나리오 작성 |  | 회장단
| 행사장 좌석배치 및 기자재 설치 | PCO
| 운영요원 배치 및 교육 | PCO
| 리허설 | PCO
VIP Room 세팅 및 행사 현장운영
식음료 및 기타 | 커피케이터링 수량 확정 및 배치
식수 준비 및 배치
참가자 기념품
VIP 기념품
경품

## Daily Program
DAY 1 - 9. 29 (Mon)
Time/Place |  | 1F |  |  | 3F |  | 5F
|  | Yeongju Hall | Baekrok Hall | Event Hall A | Halla Hall | Samda Hall | Tamna Hall A | Tamna Hall B/C | Ocean View
14:00-15:00 | 60' | Registration
14:00-18:00 | 240' |  | KSMCB Division Convergence Festival
|  |  | RNA Division & Epigenomics | Virology Molecular & Mitochondria Metabolism & Stress and Chaperone | Cell Cycle and Genome Integrity & Research for Tumor Microenvironment | Biological Rhythm & Neurodevelopmental Biology & Ciliary Organelles | Plant Molecular Biology & Microbiome
15:00-17:00 | 120' | Kick-Off Meeting (Yeongju Hall)
17:00-17:40 | 40' | General Assembly (Yeongju Hall)
DAY 2 - 9. 30 (Tue)
Time/Place |  | 1F |  |  | 3F |  | 5F
|  | Yeongju Hall | Baekrok Hall | Event Hall A | Halla Hall | Samda Hall | Tamna Hall A | Tamna Hall B/C | Ocean View
09:30-11:00 | 90` | Registration | [5 empty] | Exhibition (10:00-17:00) Poster Posting I (10:00-17:00) *Poster Presentation I (13:30-14:30) | Women in Science Mentoring for Careers in Biology and Beyond (Supported by WISET)
11:00-13:00 | 120` | S1 Neurovascular Biology Alteration of Blood Brain Barrier in Chronic Inflammation | Special Session TBD *Korean (Supported by GENINUS) | S2 Plant Cell Biology Biomolecular Condensate Dynamics in Plants | S3 Genome Medicine Advances in Cell and Gene Therapy (Supported by KMPC) | S4 Axonal Homeostasis Molecular Guardians of Neuronal Health | S5 Epigenetics in Human Disease Chromosomal Dynamics and Therapeutic Implications
13:00-14:50 | 110` | Poster Viewing
14:50-15:00 | 10` | Opening Ceremony (Tamna Hall A)
15:00-15:50 | 50` | PL1: Alan Saltiel (Tamna Hall A) Adapting to Metabolic Stress
15:50-16:10 | 20` | Break
16:10`16:40 | 30` | Ilchun Memorial Lecture (Tamna Hall A)
16:40-17:00 | 20` | KSMCB Award for Women in Life Science Lecture (Tamna Hall A)
17:00-17:20 | 20`
17:20-19:20 | 120` | [7 empty] | Welcome Reception (Award Ceremony) Ilchun Memorial Lecture/ KSMCB Award for Women in Life Science Lecture/ KSMCB Wunbong Academic Award Lecture/ KSMCB Life Science Award Lecture/ KSMCB M&C Award
DAY 3 - 10. 1 (Wed)
Time/Place |  | 1F |  |  | 3F |  | 5F
|  | Yeongju Hall | Baekrok Hall | Event Hall A | Halla Hall | Samda Hall | Tamna Hall A | Tamna Hall B/C | Ocean View
08:00-09:00 | 60` | Registration | [5 empty] | Exhibition (09:00-17:00) Poster Posting II (10:00-17:00) *Poster Presentation II (13:30-14:30)
09:00-11:00 | 120` | S6 Biotechnology Recent Trends of Cell and Gene Engineering | S7 Development & Physiology Dynamic Control of Tissue Homeostasis | S8 Plant Metabolic Engineering Advancing the Functionality and Nutritional Value of Crops | S9 Organelle Medicine Interactome Studies in Mitochondria, Lysosomes, and the ER | S10 Genomics Transforming Biology Through AI-driven Computational Genomics | S11 Cancer Metabolism Unraveling Tumor Bioenergetics and Therapeutic Targets (Joint with KSBMB)
11:00-11:20 | 20` | Break
11:20-12:10 | 50` | PL2: Anthony Hyman (Tamna Hall A) Phase Separation in Cell Physiology and Disease
12:10-13:00 (Luncheon Symposia) | 50` | Cell Safe (12:10~12:35) Bertis (12:35~13:00) | Young Investigator Session | Young Investigator Session | MERCK 350 Future Researcher Award Lectures | Deeptech Bioventure Session Beyond the Laboratory | Luncheon Symposium
13:00-14:50 | 110` | Poster Viewing
14:50-16:50 | 120` | S12 Phase Separation Biophysical Mechanisms in Cellular System | Special Session Korea BioData Station (K-BDS) From National Infrastructure to Research-Driven Applications *Korean (Supported by KOBIC/KISTI) | S13 Plant Stress Biology Advancements in Plant Stress Biology for Tackling Climate Change | S14 Memory Engram-Mediated Regulation of Emotional Memory | S15 Innovative Young Investigators in Women`s Bioscience Forum (Supported by WBF) | S16 Immunology Tissue-Resident Immune Cells in Health and Disease
16:50-17:10 | 20` | Break
17:10-18:00 | 50` | PL3: Nicolas H Thomä (Tamna Hall A) Transcription Factors in Oncology: How They Work and How to Target Them
DAY 4 - 10. 2 (Thu)
Time/Place |  | 1F |  |  | 3F |  | 5F
|  | Yeongju Hall | Baekrok Hall | Event Hall A | Halla Hall | Samda Hall | Tamna Hall A | Tamna Hall B/C | Ocean View
08:00-09:00 | 60` | Registration | [5 empty] | Exhibition (09:00-15:00)
09:00-11:00 | 120` | S17 Cancer Biology Ferroptosis and Metabolic Stress in the Tumor Microenvironment | S18 Structural Biology Frontiers in Cryo-EM Techniques and Applications | S19 Proteostasis Revisiting Protein Metabolism and Disease | S20 Autism Genetic Insights and Molecular Pathways From Multi-Model Studies | S21 Decoding Myokines Perspectives and Implications for Medicine and Drug Development | S22 Autophagy Pioneering Pathways to Therapeutic Innovations
11:00-11:20 | 20` | Break
11:20-12:10 | 50` | PL4: Michael Greenberg (Tamna Hall A) How Nature and Nurture Conspire to Control Brain Development and Function
12:10-13:00 (Luncheon Symposia) | 50` | Luncheon Symposium | Lee Se Yong Outstanding Ph.D. Thesis Award Lectures | Luncheon Symposium | Luncheon Symposium | Research Ethics Sym. *Korean | Luncheon Symposium
13:00-13:20 | 20` | Break
13:20-13:40 | 20` | KSMCB Wunbong Academic Award Lecture (Tamna Hall A)
13:40-14:10 | 30` | KSMCB Life Science Award Lecture (Tamna Hall A)
14:10-14:40 | 30` | Closing Ceremony Hanmi TGA / Excellent Poster Award / YI Research Award / Lottery / Closing Remarks (Tamna Hall A) *Korean

## 상세프로그램-숨기기 (hidden)
[프로그램 관련 자료]
날짜 | 층 | 장소 | 시간 | 상세시간 | 할당 | 세션 및 세션주제&설명 | 세션소개/강연제목 | Organizer Chair Lecturer | 소속 | 학위or직함 | 국가 | 이메일 | 휴대폰 | 계좌 | 주민등록번호 | 특이사항(국외연사료지급) | 초청레터 | 가이드 | CV | 사진 | 초록 | 발표자료 | 교 통 |  | 숙박 예약 | 호텔명 | 룸 구별 | 호수 | 인원 수 | 체크인 | 체크아웃 | 숙박 특이사항
[23 empty] | 입국 | 출국
9. 29 Mon | 1F | Baekrok Hall | 14:00-18:00 |  | 240 | RNA Division & Caenorhabditis. Elegans
|  | Event Hall A |  |  | 240 | Molecular Virology & Mitochondrion & Plant Molecular Biology
| 3F | Halla Hall |  |  | 240 | Stress and Chaperone & Epigenomics
|  | Samda Hall |  |  | 240 | Cell Cycle & Neurodevelopmental Biology & Ciliary Organelles
| 5F | Tamna Hall A |  |  | 240 | Plant molecular biology & Microbiome
| 1F | Yeongju Hall | 15:00-17:00 |  | 120 | Kick off meeting
|  |  | 17:00-17:40 |  | 40 | General assembly
9. 30 Tue | 3F | Lobby | 08:00-09:00 |  |  | Registration
| 1F | Yeongju hall | 11:00-13:00 (120) |  |  | Sym. 01 Neurovascular biology: Alteration of Blood Brain Barrier in Chronic Inflammation | Jun Young Heo |  | Department of Biochemistry, Chung Nam National University, College of medicine | M.D., Ph.D | Korea | jyheo@cnu.ac.kr |  | 하나은행, 627-910075-14507 | 810426-1480519 | 국외 연사료는 허준영 교수님께서만 사전 지급 받는 것으로 변경
[7 empty] | In June Kim |  | Graduate School of Medical Science and Engineering, Korea Advanced Institute of Science and Technology | Ph.D | Korea | injunek@kaist.ac.kr
|  |  |  | 11:00-11:30 | 30 |  | CSF flow in pervascular space and its modulation by electroceuticals | Sun Kwang Kim | College of Oriental medicine ,Kyung Hee University,. |  | Korea | skkim77@khu.ac.kr | 010-7186-1707
|  |  |  | 11:30-12:00 | 30 |  | Looking for the good: new regulators of the CNS vasculature | Junlei (Leo) Chang | Institute of Biomedicine and Biotechnology, Shenzhen Institute of Advanced Technology |  | China | jl.chang@siat.ac.
|  |  |  | 12:00-12:30 | 30 |  | TBD | Keisuke Yanagida | Department of Molecular Biology, Jikei University |  | Japan | kyanagida@ri.ncgm.go.jp
|  |  |  | 12:30-13:00 | 30 |  | TBD | Hwa Kyoung Shin | Department of Korean Medical Science/Anatomy, School of Korean Medicine, Pusan National University |  | Korea | julie@pusan.ac.kr
|  | Baekrok Hall | 11:00-13:00 (120) |  |  | Sym. 02 Women in Science: Mentoring for Careers in Biology and Beyond | * 그룹 멘토링 세션 - 멘토(연자 22명) 당 5-7명 학생 배정 - 학술대회 등록 시 관심 프로그램 체크 (시스템 구축 필요) - 사전에 연사들의 CV 취합 필요 | Seunghee Hong | Yonsei University, Department of Biochemistry | Ph.D. | Korea | seungheehong@yonsei.ac.kr |  | 우리은행, 1002-362-369992, 예금주: 홍승희 | 801118-2631710 | 사전(행사 일주일 전)에 수령
|  |  |  | 11:00-13:00 | 120 |  |  | 유경현 | 숙명여대 | 교수 | Korea | khryu@sookmyung.ac.kr
|  |  |  | 11:00-13:00 | 120 |  |  | 이은경 | 가톨릭대학교 의과대학 | 교수 | Korea | leeek@catholic.ac.kr
|  |  |  | 11:00-13:00 | 120 |  |  | 정후선 | 겐트대학교 글로벌캠퍼스 | 교수 | Korea | hoosun.chung@ghent.ac.kr
|  |  |  | 11:00-13:00 | 120 |  |  | 권순경 | 경상국립대학교 | 교수 | Korea | skkwon@gnu.ac.kr
|  |  |  | 11:00-13:00 | 120 |  |  | 서지혜 | 계명대학교 의과대학 | 교수 | Korea | seojihae7@gmail.com
|  |  |  | 11:00-13:00 | 120 |  |  | 박현정 | 서울대학교 | 교수 | Korea | charl4009@snu.ac.kr
|  |  |  | 11:00-13:00 | 120 |  |  | 김윤주 | 연세대학교 시스템생물학과 | 교수 | Korea | yunjukim@yonsei.ac.kr
|  |  |  | 11:00-13:00 | 120 |  |  | 임선아 | 이화여자 대학교 생명과학과 | 교수 | Korea | seonlim@ewha.ac.kr
|  |  |  | 11:00-13:00 | 120 |  |  | 최지은 | 제주대학교 수의학과 | 교수 | Korea | choige@jejunu.ac.kr
|  |  |  | 11:00-13:00 | 120 |  |  | 이지민 | 카이스트 의과학대학원 | 교수 | Korea | jimin.lee@kaist.ac.kr
|  |  |  | 11:00-13:00 | 120 |  |  | 박현지 | 아주대학교 | 교수 | Korea | hyunjipark@ajou.ac.kr
|  |  |  | 11:00-13:00 | 120 |  |  | 정진영 | 한국생명공학연구원 | 연구소 | Korea | nuciferajin@gmail.com
|  |  |  | 11:00-13:00 | 120 |  |  | 신예지 | GC녹십자 | 회사 | Korea | syj910130@gccorp.com
|  |  |  | 11:00-13:00 | 120 |  |  | 김다예 | 대구경북첨단의료산업진흥재단 신약개발지원센터 | 연구소 | Korea | dayea23@hanmail.net
|  |  |  | 11:00-13:00 | 120 |  |  | 김영혜 | 한국기초과학지원연구원 디지털오믹스연구부 | 연구소 | Korea | yhkim74@kbsi.re.kr
|  |  |  | 11:00-13:00 | 120 |  |  | 김은미 | 국립암센터 | 연구소 | Korea | emkim@ncc.re.kr
|  |  |  | 11:00-13:00 | 120 |  |  | 서진주 | 한국과학기술연구원 | 연구소 | Korea | jinjuseo@kist.re.kr
|  |  |  | 11:00-13:00 | 120 |  |  | 오경진 | 한국생명공학연구원/대사제어연구센터 | 연구소 | Korea | kjoh80@kribb.re.kr
|  |  |  | 11:00-13:00 | 120 |  |  | 이선주 | 대구경북첨단의료산업진흥재단 | 연구소 | Korea | disjrk@kmedihub.re.kr
|  |  |  | 11:00-13:00 | 120 |  |  | 조이숙 | 한국생명공학연구원 면역치료제연구센터 | 연구소 | Korea | june@kribb.re.kr
|  |  |  | 11:00-13:00 | 120 |  |  | 한정현 | 베링거인겔하임 | 회사 | Korea | june.hahn@boehringer-ingelheim.com
|  |  |  | 11:00-13:00 | 120 |  |  | 박은영 | 에이인비, AinB INC. | 회사 | Korea | eunyoung.park@ainbsci.com
|  | Event Hall A | 11:00-13:00 (120) |  |  | Sym. 03 Biomolecular Condensate Dynamics in Plants | Woe Yeon Kim |  | Gyeongsang National University, Division of Applied Life Sciences | PhD | Korea | kim1312@gnu.ac.kr |  | 농협, 818-02-482874 | 690428-2829813 | 행사 후, 연사 계좌로 입금
|  |  |  | 11:00-11:30 | 30 |  | TBD | Caiji GAO | South China Normal University |  | China | gaocaiji@m.scnu.edu.cn
|  |  |  | 11:30-11:55 | 25 |  | TBD | Il Doo Hwang | POSTECH |  | Korea | ihwang@postech.ac.kr
|  |  |  | 11:55-12:20 | 25 |  | TBD | Xiaofeng Fang | Tsinghua University |  | China | xffang@tsinghua.edu.cn
|  |  |  | 12:20-12:45 | 25 |  | TBD | Jong-Seong Jeon | Kyung Hee University |  | Korea | jjeon@khu.ac.kr
|  |  |  | 12:45-13:00 | 15 |  | GI regulates acquired thermotolerance by forming cytosolic condensate formation | Gyeong Ik Ahn | Gyeongsang National University |  | Korea | ahngi@gnu.ac.kr
| 3F | Halla Hall | 11:00-13:00 (120) |  |  | Sym. 04 KMPC(국가모델동물연구소) | Kyoungmi Kim |  | Korea University | PhD | Korea | kim0912@korea.ac.kr |  | 신한은행 (110-203-571215) | 821115-2324017
[7 empty] | Ho Lee |  | National Cancer Center | PhD | Korea | ho25lee@ncc.re.kr
|  |  |  | 11:00-11:30 | 30 |  | TBD | Dali LI (미정) | East China Normal University |  | China | dlli@bio.ecnu.edu.cn
|  |  |  | 11:30-11:55 | 25 |  | TBD | 지헌영 | Yonsei University |  | Korea | hygee@yuhs.ac | 010-3637-0196
|  |  |  | 11:55-12:20 | 25 |  | TBD | 이현지 | Korea University |  | Korea | hjlee102@korea.ac.kr | 010-2736-2384
|  |  |  | 12:20-12:45 | 25 |  | TBD | 유용진 | Korea University |  | Korea | yongjinyoo@korea.ac.kr | 010-5235-7504
|  |  |  | 12:45-13:00 | 15 |  | TBD | 엄희수(Young Scientist) | Seoul National University |  | Korea | Heesoo.Uhm@gmail.com | 010-8751-2849
|  | Samda Hall | 11:00-13:00 (120) |  |  | Sym. 05 The Link Between Miocrobiota and Neuodegeneration
| 5F | Tamna Hall A | 11:00-13:00 (120) |  |  | Sym. 06 Epigenetics in Human Disease: Chromosomal Dynamics and Therapeutic Implications | Inkyung Jung |  | Department of Biological Sciences, KAIST | Ph.D. | Korea | ijung@kaist.ac.kr |  | 국민은행 정인경 748301-01-590357: 국외연자비, 세션 운영비 | 830415-1070921 | 사전(행사 일주일 전)에 수령 요망: 오거나이저 계좌로 입금 (원화)
[7 empty] | Hong-Duk Youn |  | Seoul National University, College of Medicine | Ph.D. | Korea | hdyoun@snu.ac.kr |  | 윤홍덕 교수님 계좌: 좌장비
|  |  |  | 11:00-11:25 | 25 |  | Epigenetic Mechanisms Underlying Social Behavior in Autism Spectrum Disorder | Tae-Kyung Kim | Department of Life Sciences, Pohang University of Science and Technology |  | Korea | tkkim@postech.ac.kr
|  |  |  | 11:25-11:50 | 25 |  | How a differentiation gene acquires oncogenic potential? | Chul-Hwan Lee | Seoul National University, College of Medicine |  | Korea | chulhwan@snu.ac.kr
|  |  |  | 11:50-12:15 | 25 |  | Chromosome regulations in neurodevelopmental disorders | Guoqiang Li | Biomedical Pioneering Innovation Center,Peking University |  | China | liguoqiang@pku.edu.cn
|  |  |  | 12:15-12:35 | 20 |  | Chromatin dynamics and DNA damage response in maintaining genome integrity | Sunwoo Min | Department of Biochemistry, College of Natural Sciences, Chungnam National University |  | Korea | smin1221@cnu.ac.kr
|  |  |  | 12:35-12:55 | 20 |  | Chromatin Remodeling in Blood Cells and Therapeutic Implications | Hye Ji Cha | Dankook University |  | Korea | hyejicha@dankook.ac.kr
|  | Tamna Hall BC | 13:00-14:50 |  | 110 | Poster viewing
|  | Tamna Hall A | 14:50-15:00 |  | 10 | Opening ceremony
|  | Tamna Hall A | 15:00-15:50 |  | 50 | PL 1 |  | Alan Saltiel | UCSD |  | USA
|  |  | 15:50-16:10 |  | 20 | Break
|  | Tamna Hall A | 16:10-16:40 |  | 30 | Ilchun memorial lecture
|  | Tamna Hall A | 16:40-17:00 |  | 20 | KSMCB award for women in life science lecture
|  |  | 17:00-17:20 |  | 20 | Break
|  | Ocean view | 17:20-19:20 |  | 120 | Welcome reception
|  | Tamna Hall BC |  |  |  | Exhibition(10:00-17:00) / Poster postingⅠ (10:00-17:00) / *Poster presentationⅠ(13:30-14:30)
10. 1 Wed | 3F | Lobby | 08:00-09:00 |  | 60 | Registration
| 1F | Event Hall A | 09:00-11:00 |  |  | Sym. 07 Biotechnology: Recent Trends of Cell and Gene Engineering | Sangsu BAE |  | Seoul National University College of Medicine | Ph.D. | Korea | sbae7@snu.ac.kr |  | 농협, 079-12-229138 | 800208-1644022 | 사전(행사 일주일 전)에 수령 요망: 오거나이저 계좌로 입금 (원화)
|  |  |  | 9:00-9:30 | 30 |  | From Gene Editing to New Frontiers: Advancing Cell and Gene Therapies | Wensheng Wei | Peking University |  | China | wswei@pku.edu.cn
|  |  |  | 9:30-9:55 | 25 |  | Gene editing in human pluripotent stem cells for ex vivo stem cell therapy | (차혁진)Hyuk-Jin Cha | 서울대학교 |  | Korea | hjcha93@snu.ac.kr | 010-7655-7251
|  |  |  | 9:55-10:20 | 25 |  | Development of lipid Nanoparticles for in vivo delivery of mRNA vaccines and therapeutics | (이혁진) Hyukjin Lee | 이화여자대학교 |  | Korea | hyukjin@ewha.ac.kr | 010-9166-9565
|  |  |  | 10:20-10:40 | 20 |  | Base editing to treat genetic hearing loss | (이상연) Sang-Yeon Lee | 서울대병원 |  | Korea | maru4843@hanmail.net | 010-3645-9715
|  |  |  | 10:40-11:00 | 20 |  | Advancing Specificity and Versatility in Genome Editing Technologies | (임가영) Kayeong Lim | 한국과학기술연구원(KIST) |  | Korea | kylim@kist.re.kr | 010-9500-6077
|  | Yeongju Hall | 09:00-11:00 |  |  | Sym. 08 Development & Physiology: Dynamic Control of Tissue Homeostasis | Seyun Kim |  | Dept. Biological Sciences, Korea Advanced Institute of Science and Technology | Ph.D. | Korea | seyunkim@kaist.ac.kr |  | 우리은행 1002-745-463981 | 731225-1063718 | 행사 후, 연사 계좌로 입금
|  |  |  | 9:00-9:25 | 25 |  | Myeloid blood cells in metabolic and physiological homeostasis | 심지원 | 서울대학교 생명과학부 |  | Korea | jshim@hanyang.ac.kr | 010-5223-6629
|  |  |  | 9:25-9:50 | 25 |  | A gut microbiota-secreted protein Amuc_1409 contributes to the maintenance of gut health | 이철호 | 생명공학연구원 |  | Korea | chullee@kribb.re.kr | 010-3411-4637
|  |  |  | 9:50-10:15 | 25 |  | Morphogenesis of extracellular matrix (ECM): Roles of cell surface shape in matrix assembly | 박성진 | University of Utah |  | Korea | sungjin.park@neuro.utah.edu | (+1)801-581-6106
|  |  |  | 10:15-10:40 | 25 |  | Hippo-YAP/TAZ signaling and adipocyte plasticity | 임대식 | 한국과학기술원 |  | Korea | daesiklim@kaist.ac.kr | 010-4271-1555
|  | Baekrok Hall | 09:00-11:00 |  |  | Sym. 09 Plant Metabolic Engineering: Advancing the Functionality and Nutritional Value of Crops | Sun-Hwa, HA |  | College of Life Sciences, Kyung Hee University | Ph.D. | Korea | sunhwa@khu.ac.kr |  | 농협중앙회, 125-12-138390 | 680423-2670318 | 행사 후, 연사 계좌로 입금 *국외 연사비 수령 방법은 향후 변경 요청될 수 있음
|  |  |  | 09:00-09:25 | 25 |  | Plant Specialized Metabolism and Synthetic biology for terpenoids production | Moonhyuk Kwon | Gyeongsang National University |  | Korea | moonhyukkwun@gmail.com | 010-5943-6878
|  |  |  | 09:25-10:05 | 40 |  | Carotenoid | Manuel Rodriguez-Concepcion | Institute for Plant Molecular and Cell Biology (IBMCP), CSIC-Universitat Politècnica de València, Spain |  | Spain | manuelrc@ibmcp.upv.es | 34645507345
|  |  |  | 10:05-10:30 | 25 |  | Deciphering Regulatory Networks Governing Flavonoid Metabolic Flux in Plants | Sun-Hyung Lim | Hankyong National University |  | Korea | limsh2@hknu.ac.kr | 010-7339-6752
|  |  |  | 10:30-10:55 | 25 |  | Enhancing Vegetable Oil Quality: Balancing Fatty Acid Composition for Health and Stability | Hyun Uk Kim | Sejong University |  | Korea | hukim64@sejong.ac.kr | 010-6828-1232
| 3F | Halla Hall | 09:00-11:00 |  |  | Sym. 10 Organelle Medicine: Interactome Studies in Mitochondria, Lysosomes, and the ER | Kyu-Sang Park |  | Yonsei University Wonju College of Medicine | M.D., Ph.D. |  | qsang@yonsei.ac.kr |  | 신한은행 100-025-441865 | 690904-1807611 | 사전(행사 일주일 전)에 수령 요망
|  |  |  | 9:00-9:10 | 10 |  | Session Overview | 박규상 | 연세대학교 원주의과대학 |  | Korea | qsang@yonsei.ac.kr | 010-2655-4071
|  |  |  | 9:10-9:40 | 30 |  | Recording and writing activity history into living cells | Christina Kim | Princeton University, USA |  | USA | ckk@princeton.edu
|  |  |  | 9:40-10:10 | 30 |  | Molecular mechanism to control lysosomal homeostasis by autophagy in aging and diseases | Shuhei Nakamura | Nara Medical University, Japan |  | Korea | shuhei.nakamura@naramed-u.ac.jp
|  |  |  | 10:10-10:35 | 25 |  | Targeting roles of lysosomal TM4SF5 in hepatocellular carcinogenesis | 이정원 | 서울대학교 약학대학 |  | Korea | jwl@snu.ac.kr
|  |  |  | 10:35-11:00 | 25 |  | A Mitochondrial Switch for Cell Fate Decision in Early Corticogenesis | 박상기 | 포항공과대학교 |  | Korea | skpark@postech.ac.kr
|  | Samda Hall | 09:00-11:00 |  |  | Sym. 11 한국파스퇴르연구소
| 5 | Tamna Hall A | 09:00-11:00 |  |  | Sym. 12 Cancer Metabolism: Unraveling Tumor Bioenergetics and Therapeutic Targets | Heon Yung Gee |  | Yonsei University College of Medicine | M.D./Ph.D. / Ph.D. | Korea | hwp003@yonsei.ac.kr |  | 우리은행 1002-961-516338 | 780115-1357623 | 행사 후, 연사 계좌로 입금
[7 empty] | Hyun Woo Park |  | Yonsei University College of Life Science and Biotechnology |  | Korea | hygee@yuhs.ac.kr
|  |  |  | 9:00-9:25 | 25 |  | TBD | Yun Pyo Kang | Seoul National University |  | Korea | yunpyo.kang@snu.ac.kr
|  |  |  | 9:25-9:50 | 25 |  | TBD | Hyun Woo Park | Yonsei University |  | Korea | HWP003@YONSEI.AC.KR | 010-4128-0746
|  |  |  | 9:50-10:20 | 30 |  | TBD | Dohoon Kim | University of Massachusetts Chan Medical School |  | Korea | dohoon.kim@umassmed.edu | 010-4396-4338
|  |  |  | 10:20-10:45 | 25 |  | TBD | Soo-Youl Kim | National Cancer Center |  | Korea | kimsooyoul@gmail.com | 010-4657-4369
|  |  | 11:00-11:20 |  | 20 | Break
| 5 | Tamna Hall A | 11:20-12:10 |  | 50 | PL 2 |  | Anthony Hyman | Department of Cellular organization by phase separation, Max Planck Institute of Molecular Cell Biology & Genetics | Ph.D. | British | hyman@mpi-cbg.de
| 1F | Yeongju hall | 12:10-13:00 |  | 50 | Luncheon Sym.
|  | Baekrok hall |  |  | 50 | Young investigator session
|  | Event hall A |  |  | 50 | Young investigator session
| 3F | Halla hall |  |  | 50 | MERCK 350 future researcher award lectures
| 5F | Tamna Hall A |  |  | 50 | Luncheon
| 3F | Samda hall | 12:00-14:50 |  | 50 | Bioventure session
| 5F | Tamna Hall BC | 13:00-14:50 |  | 110 | Poster viewing
| 1F | Yeongju Hall | 14:50-16:50 |  |  | Sym. 13 Phase Separation: Biophysical Mechanisms in Cellular System | Joo-Yeon Yoo |  | Pohang University of Science and Technology, Department of Life Scienes | Ph.D. |  | jyoo@postech.ac.kr |  | 국민은행 594202-04-028497 | 670210-2019741 | 행사 후, 연사 계좌로 입금
|  |  |  | 14:50-15:15 | 25 |  | The flow of genetic information and biomolecular condensation | 신용대 | 서울대학교 |  | Korea | ydshin@snu.ac.kr | 010-5386-0415
|  |  |  | 15:15-15:35 | 20 |  | Liquid-liquid phase separation and its role in regulating living systems | 이종찬 | DGIST |  | Korea | jclee@dgist.ac.kr | 010-7301-1716
|  |  |  | 15:35-16:05 | 30 |  | Sequence Composition Dictates Condensate Miscibility | Pilong Lee | Tsinghua University |  | China | pilongli/@mail.tsinghua.edu.cn
|  |  |  | 16:05-16:30 | 25 |  | LLPS Based on the Biophysical and Biochemical Properties of Amino Acids | 황동수 | 포스텍 |  | Korea | dshwang@postech.ac.kr | 010-4168-2976
|  |  |  | 16:30-16:50 | 20 |  | Altered dynamics of nuclear condensates under cellular senescence | 권영대 | 성균관대학교 |  | Korea | ygwon@skku.edu | 010-2812-0826
|  | Baekrok Hall | 14:50-16:50 |  |  | Sym. 14 Transforming Biology Through AI-driven Computational Genomics | Soon-Kyeong Kwon |  | Division of Life Science, Gyeongsang National University | Ph.D. | Korea | skkwon@gnu.ac.kr |  |  |  | 행사 후, 연사 계좌로 입금
[7 empty] | Hyobin Jeong |  | Department of Systems Biology, Yonsei University | Ph.D. | Korea | hyobinjeong@yonsei.ac.kr |  | 우리은행 1002-353-640185 (정효빈) | 890920-2054310 (정효빈)
|  |  |  | 14:50-15:15 | 25 |  | TBD | Martin Steinegger | Seoul National Universtiy |  | Korea | martin.steinegger@snu.ac.kr | 010-2862-2673
|  |  |  | 15:15-15:40 | 25 |  | TBD | Michael Stadler | Friedrich Miescher Institute for Biomedical Research |  | Switzerland | michael.stadler@fmi.ch
|  |  |  | 15:40-16:05 | 25 |  | MAZ-mediated speckle-genome interactions in chromatin reorganization | Inkyung Jung | Korea Advanced Institute of Science and Technology |  | Korea | ijung@kaist.ac.kr | 010-3327-2852
|  |  |  | 16:05-16:30 | 25 |  | TBD | Young-suk Lee | Korea Advanced Institute of Science and Technology |  | Korea | youngl@kaist.ac.kr | -8234
|  |  |  | 16:30-16:55 | 25 |  | TBD | Jihwan Park | Ajou University |  | Korea | parkjihwan@ajou.ac.kr | 010-9455-9209
|  | Event hall A | 14:50-16:50 |  |  | Sym. 15 Plant Stress Biology: Advancements in Plant Stress Biology for Tackling Climate Change | Choon-Tak Kwon |  | Kyung Hee University / College of Life Sciences | Ph.D. | Korea | ctkwon@khu.ac.kr |  | 농협중앙회 079-12-705595 권춘탁 | 860101-1025415 | 행사 후, 연사 계좌로 입금
[7 empty] | Dae-Jin Yun |  | Konkuk University / Institute of Science and Technology | Ph.D. | Korea
|  |  |  | 14:50-15:15 | 25 |  | Temperature-Controlled Liquid–Liquid Phase Separation Underlies Thermoresponsive Flowering in Arabidopsis | 서필준 Seo, Pil Joon | 서울대학교 Seoul National University |  | Korea | pjseo1@snu.ac.kr | 010-2644-3200
|  |  |  | 15:15-15:40 | 25 |  | Stress Responses Regulated by Brassinosteroid Signaling in Arabidopsis | 김태욱 Kim, Tae-Wuk | 한양대학교 Hanyang University |  | Korea | twgibio@hanyang.ac.kr | 010-6335-2547
|  |  |  | 15:40-16:10 | 30 |  | Impact of invisible light in crop development: UV-B on rice | Xu, Zheng Yi | Northeast Normal University, China |  | China | xuzy100@nenu.edu.cn
|  |  |  | 16:10-16:30 | 20 |  | Cold Stress Induced Dynamic Chromatin Accessibility Facilitates Histone Reorganization and Transcription Factor Recruitment in Arabidopsis | 박정훈 Park, Junghoon | 건국대학교 Konkuk University |  | Korea | p6259j@gmail.com | 010-8544-6259
|  |  |  | 16:30-16:50 | 20 |  | Beyond Temperature: Decoding Plant Thermomorphogenesis | 이상화 Lee, Sanghwa | 연세대학교 Yonsei University |  | Korea | shuslee89@gmail.com | 010-9264-0500
| 3F | Halla Hall | 14:50-16:50 |  |  | Sym. 16 Engram-mediated Regulation of Emotional Memory | KIM, Joung Hun |  | POSTECH | PhD | Korea | joungkim@postech.ac.kr |  | 하나은행 13691011038007 | 661221-1010511 | 행사 후, 연사 계좌로 입금
|  |  |  | 14:50-15:20 | 30 |  | Molecular and circuit mechanisms of cerebellar modulation of classical fear conditioning | Yong-Seok Lee | Seoul National University College of Medicine |  | Korea | yongseok7@snu.ac.kr | 010-3916-6316
|  |  |  | 15:20-15:50 | 30 |  | Neuronal Recruitment and Synaptic Connectivity: Mechanisms Underpinning Engram Formation in Functional Brain Networks | Ron Stoop | University of Lausanne, Swiss |  | Switzerland | ron.stoop@unil.ch
|  |  |  | 15:50-16:20 | 30 |  | Same cue same neuron; Insights into How Experiences Shape Our Memories | Jung Hoon Jung | Keimyung University College of Pharmacy |  | Korea | jungjh@kmu.ac.kr | 010-8119-5783
|  |  |  | 16:20-16:50 | 30 |  | A deep neural network approach to understand aversive learning and behavior | HyungGoo Kim | Sungkyunkwan University |  | Korea | hyunggoo.r.kim@gmail.com | 010-3968-5171
|  | Samda Hall | 14:50-16:50 |  |  | Sym. 17 Innovative Young Investigators in Women’s Bioscience Forum | Youngmi Jung |  | College of Natural Sciences, Pusan National University | Ph.D | Korea | y.jung@pusan.ac.kr |  | 농협 302-0181-725561 | 730730-2018115 | 행사 후, 연사 계좌로 입금
|  |  |  | 14:50-15:20 | 30 |  | Pollutant-Induced Alteration in the Gut Microenvironment and Development of Allergy | 김은수 | 부산대학교 |  | Korea | eunsoo_kim@pusan.ac.kr | 010-3144-4016
|  |  |  | 15:20-15:50 | 30 |  | Exploring Immune Synaptosomes: Potential Applications in Immune Cell Therapy | 김혜란 | 국립암센터 |  | Korea | hrki@ncc.re.kr | 010-5209-6811
|  |  |  | 15:50-16:20 | 30 |  | C/EBP⍺ activates Irf8 expression in myeloid progenitors at the +56 kb enhancer to initiate cDC1 development | 김선경 | 아주대학교 |  | Korea | dcbio@ajou.ac.kr | 010-9483-1354
|  |  |  | 16:20-16:50 | 30 |  | Unveiling the Mechanism of an Intramembrane chaperone for multipass membrane proteins | 김민경 | 가천대학교 |  | Korea | minkim@gachon.ac.kr | 010-3415-0524
| 5F | Taman Hall A | 14:50-16:50 |  |  | Sym. 18 Immunology: Tissue-Resident Immune Cells in Health and Disease | Hye Young Kim |  | Seoul National University College of Medicine | Ph.D. | Korea | hykim11@snu.ac.kr |  | (신한)110-335-938100 | 780807-2149411 | 행사 후, 연사 계좌로 입금
|  |  |  | 14:50-15:05 | 15 |  | Overview | 김혜영 | 서울대학교 의과대학 |  | Korea | Hykim11@snu.ac.kr | 010-2428-7870
|  |  |  | 15:05-15:35 | 30 |  | TBD | Kiyoshi Hirahara | Chiba university |  | Japan | hiraharak@chiba-u.jp
|  |  |  | 15:35-16:00 | 25 |  | TBD | 김유미 | KAIST 의과학대학원 |  | Korea | youmekim@kaist.ac.kr | 010-9552-2560
|  |  |  | 16:00-16:25 | 25 |  | TBD | 배외식 | 성균관대학교 생명과학과 |  | Korea | yoesik@skku.edu | 010-7166-2547
|  |  |  | 16:25-16:50 | 25 |  | TBD | 최제민 | 한양대학교 생명과학과 |  | Korea | jeminchoi@hanyang.ac.kr | 010-9046-7765
|  |  | 16:50-17:10 |  | 20 | Break
| 5F | Taman Hall A | 17:10-18:00 | 17:10-18:00 | 50 | PL 4 | Transcription factors in oncology: how they work and how to target them | Nicolas H Thomä | Paternot Professorship at EPFL/ISREC School of Life Sciences |  | Switzerland | nicolas.thoma@epfl.ch
| 5F | Tamna Hall BC |  |  |  | Exhibition(09:00-17:00) / Poster postingⅠ (10:00-17:00) / *Poster presentationⅠ(13:30-14:30)
10. 2 Thu | 3F | Lobby | 08:00-09:00 |  | 60 | Registration
| 1F | Event Hall A | 09:00-11:00 |  |  | Sym. 19 Ferroptosis and Metabolic Stress in the Tumor Microenvironment | Jun-Young Seo |  | Yonsei University College of Medicine | Ph.D. | Korea | jyseo0724@yuhs.ac |  | 우리은행 1002-548-271119 | 720724-1690210 | 행사 후, 연사 계좌로 입금 a. Bank: Postbank b. Account holder: José Friedmann Angeli c. IBAN: DE28 6001 0070 0781 6137 03
[7 empty] | 김광석 |  |  |  | Korea | kskim@kirams.re.kr
|  |  |  | 09:00-09:30 | 30 |  | A potential mechanism of ferroptosis resistance in immune-refractory tumor cells | Kwon-Ho Song (송권호) | Daegu Catholic University (대구가톨릭대학교) |  | Korea | khsong@cu.ac.kr | 010-6761-4578
|  |  |  | 09:30-10:00 | 30 |  | TGF-β2-mediated ferrous ion imbalance drives ferroptotic cell death of salivary gland acinus in postmenopausal conditions | Hyung-Sik Kim (김형식) | Pusan National University (부산대학교) |  | Korea | hskimcell@pusan.ac.kr | 010-8533-3922
|  |  |  | 10:00-10:30 | 30 |  | Emerging mechanism determining tolerance to phospholipid peroxidation and ferroptosis resistance. | José Pedro Friedmann Angeli | University of Würzburg |  | Germany | pedro.angeli@uni-wuerzburg.de | (+49) 01520 1317345
|  |  |  | 10:30-11:00 | 30 |  | Selenium's Paradox in Ferroptosis: A Double-Edged Sword in Cancer Microenvironments | Namgyu Lee (이남규) | Dankook University (단국대학교) |  | Korea | namgyu.lee@dankook.ac.kr | 010-5953-3880
|  | Yeongju Hall | 09:00-11:00 |  |  | Sym. 20 Structural Biology: Frontiers in Cryo-EM Techniques and Applications | Sangho Lee |  | Department of Biological Sciences, College of Natural Sciences, Sungkyunkwan University | Ph.D. | Korea | sangholee@skku.edu |  | 우리은행, 1002-334-396882 | 691009-1052413 | 행사 후, 연사 계좌로 입금
|  |  |  | 09:00-09:05 | 5 |  | (Introduction) (ALTERNATIVELY, this time block will serve as a buffering zone for over-timing talks) | Chair (TBA)
|  |  |  | 09:05-09:30 | 25 |  | Cryo-EM study for the development of antiviral drugs and vaccines | Katsumi Maenaka | Hokkaido University, Japan |  | Japan | maenaka@pharm.hokudai.ac.jp
|  |  |  | 09:30-09:55 | 25 |  | TBD | Jose Rodriguez | University of California, Los Angeles (UCLA), USA |  | USA | jrodriguez@mbi.ucla.edu
|  |  |  | 09:55-10:20 | 25 |  | Structural mechanisms for regulating anion channels in plants | Sangho Lee | Sungkyunkwan University, Korea |  | Korea | sangholee@skku.edu | 010-8628-7535
|  |  |  | 10:20-10:40 | 20 |  | Computational Tools and algorithms in scipionTomo for cryo-electron Tomography Image Processing | Jose Luis Vials Prieto | Consejo Superior de Investigaciones Científicas (CSIC, Spanish National Research Council), Spain |  | Spain | jlvilas@cnb.csic.es
|  |  |  | 10:40-11:00 | 20 |  | Structural insights into TRPV4-Rho GTPase signaling complex function and disease | Dohoon Kwon | POSTECH, Korea |  | Korea | Dohoon.kwon@duke.edu
|  | Baekrok Hall | 09:00-11:00 |  |  | Sym. 21 Proteostasis: Revisiting Protein Metabolism and Disease | 황철상 |  |  |  | Korea | hwangcs@korea.ac.kr
[7 empty] | Young Joo Jeon |  | Chungnam National University College of Medicine | Ph.D. | Korea |  |  | 하나은행, 627-910189-82407 | 740510-2006029 | 사전(행사 일주일 전)에 수령 요망: 오거나이저 계좌로 입금 (원화)
|  |  |  | 09:00-09:25 | 25 |  | The roles of the protein homeostasis system in the development of NASH | Jaewhan Song (송재환) | Department of Biochemistry, College of Life Science and Technology (연세대학교 생화학과) |  | Korea | jso678@yonsei.ac.kr | 010-3004-9544
|  |  |  | 09:25-09:50 | 25 |  | Ubiquitin in signaling: a tale of atypical linear ubiquitin chains | Kazuhiro Iwai | Graduate School of Medicine, Kyoto University (Provost, Vice President of Kyoto University) |  | Japan | iwai.kazuhiro.4e@kyoto-u.ac.jp (kiwai@mcp.med.kyoto-u.ac.jp) | -9788
|  |  |  | 09:50-10:15 | 25 |  | Decoding of ER Ca2+ transients to trigger autophagosome formation | Hong Zhang | Institute of Biophysics, Chinese Academy of Sciences |  | China | hongzhang@ibp.ac.cn | -13269509402
|  |  |  | 10:15-10:40 | 25 |  | From concept to application: the fundamentals of PROTAC discovery | Kwang-Su Park (박광수) | Keimyung University College of Pharmacy (계명대학교 약학대학) |  | Korea | parkks@kmu.ac.kr | 010-4611-0694
| 3F | Halla Hall | 09:00-11:00 |  |  | Sym. 22 Autism: Genetic Insights and Molecular Pathways From Multi-Model Studies | Hee Jeong Yoo |  | Seoul National University College of Medicine | M.D., Ph.D. | Korea | hjyoo@snu.ac.kr |  | 신한은행 36704-712072, 유희정 | 700814-2235016 | 사전(행사 일주일 전)에 수령 요망: 오거나이저 계좌로 입금 (원화)
[8 empty] | Sung-Oh Huh | Hallym University College of Medicine | Ph.D. | Korea | s0huh@hallym.ac.kr | 010-9359-2615
|  |  |  | 09:00-09:25 | 25 |  | Genetic Heterogeneity of Autism: Lessons Learned from Korean Autism Genome Studies | Joon-Yong An | Korea University, Department of Biomedical and Biosciences, |  | Korea | joonan30@korea.ac.kr | 010-7248-6840
|  |  |  | 09:25-09:50 | 25 |  | Modeling autism spectrum disease with neurons and organoids derived from generically modified iPSC | Ji Yeon Lee | Seoul National University College of Medicine |  | Korea | ddang1@snu.ac.kr | 010-4253-0283
|  |  |  | 09:50-10:15 | 25 |  | Regulation of Presynaptic Homeostatic Plasticity by Autism-Related Genes | Seungbok Lee | Seoul National University School of Dentistry |  | Korea | seunglee@snu.ac.kr | 010-3390-2580
|  |  |  | 10:15-10:40 | 25 |  | Post-Exome Genetics and Genomics Studies of ASD | Atsushi Takata | RIKEN Center for Brain Science, Laboratory for Molecular Pathology of Psychiatric Disorders |  | Japan | atsushi.takata@riken.jp | #ERROR!
|  |  |  | 10:40-11:00 | 20 |  | Q & A
|  | Samda Hall | 09:00-11:00 |  |  | Sym. 23 Decoding Myokines: Perspectives and Implications for Medicine and Drug Development | JEE HOON ROH |  | Department of Physiology, Korea University College of Medicine | M.D., Ph.D. | Korea | alzheimer@korea.ac.kr |  | KEB 하나 576-810142-50607 | 780928-1012217 | 행사 후, 연사 계좌로 입금
|  |  |  | 09:00-09:20 | 20 |  | Decoding Myokines: Myokine Convergence Research Center | 김현수 | 고대의대 해부학교실 |  | Korea | anatomykim@korea.ac.kr | 010-9802-1226
|  |  |  | 09:20-09:45 | 25 |  | Irisin-Mediated Amyloid-β Reduction via ERK-STAT3 Downregulation | 김은희 | 고대의대 생리학교실 |  | Korea | kimneuroscience@gmail.com | 010-9265-8464
|  |  |  | 09:45-10:05 | 25 |  | Senescence and Muscle Health: Implicaitons for Age-Related Disease and Therapeutics | 전옥희 | 고대의대 융합의학교실 |  | Korea | ojeon@korea.ac.kr | 010-9296-6109
|  |  |  | 10:05-10:30 | 25 |  | Application of Engineered Cas Protein and VLP Based Delivery Method in Gene Editing | 김경미 | 고대의대 생리학교실 |  | Korea | kim0912@korea.ac.kr | 010-8389-6379
|  |  |  | 10:30-10:55 | 25 |  | Identification of gero-protective myokines using 3D microphysiological system | 장영목 | 에모리대학 정형외과 |  | Korea | young.jang@emory.edu | (+1)404-251-457
| 5F | Tamna Hall A | 09:00-11:00 |  |  | Sym.24 Autophagy: Pioneering Pathways to Therapeutic Innovations | Eun-Kyeong Jo |  | Chungnam National University, College of Medicine | M.D., Ph.D. | Korea | hayoungj@cnu.ac.kr |  | 하나은행 621-679080-00108 조은경 | 670423-2408526 | 행사 후, 연사 계좌로 입금
|  |  |  | 09:00-09:20 | 20 |  | Autophagic regulation of stress granules associated with neurological disorders | Jin-A Lee | Hannam University |  | Korea | leeja@hnu.kr | 010-3100-0611 |  |  | 김도형 박사님: (숙박 포함) 150만원 드릴 수 있도록 하겠습니다 Han-Ming Shen 박사님: (숙박 포함) 150만원 드릴 수 있도록 하겠습니다 ----------- - 본 세션은 공동좌장으로 충남대 조은경 교수와 경북대 조동형 교수 2인이 하도록 하겠습니다. - 5,6은 short talk으로 조동형교수님과 서울대 정용근 교수님 두분 포닥들이신데 아주 훌륭한 연구를 하셔서 main talk은 아니지만 심포지엄이 빛날 것 같습니다. 국내 연사는 4분 지원해 주시는 것으로 알고 있습니다. 두분 short talk을 하시는 연사분들은 따로 지원해 주시지 않으셔도 저희 연구단에서 각각 support를 할 수 있도록 하겠습니다. - 저희 연구단에서 학회 공동 주관 심포지엄으로 300만원 지원 예정입니다
|  |  |  | 09:20-09:45 | 25 |  | Differential autophagy responses to amino acid versus energy deficiencies | Do-Hyung Kim | Department of Biochemistry, Molecular Biology, and Biophysics, University of Minnesota Twin Cities |  | USA | dhkim@umn.edu | (+1)-612-626-3418
|  |  |  | 09:45-10:10 | 25 |  | Regulation of PINK1, from transcription and post-translational modifications | Han-Ming Shen | Faculty of Health Sciences, University of Macau |  | Macau(China) | hmshen@um.edu.mo
|  |  |  | 10:10-10:30 | 20 |  | p53 protects adult hippocampal neural stem cells from psychological stress by inhibiting autophagic cell death | Seong-Woon Yu | Faculty of Health Sciences, University of Macau |  | Korea | yusw@dgist.ac.kr | 010-4591-2967
|  |  |  | 10:30-10:45 | 15 |  | Selective autophagy for Lysosome: Novel regulation mechanism of lysophagy by TBK1-SCFFBXO3-TMEM192-TAX1BP1 axis | Na Yeon Park | Department of Brain Sciences, DGIST |  | Korea | Yeonie5613@gmail.com | 010-6385-4834
|  |  |  | 10:45-11:00 | 15 |  | UBXN6-mediated autophagy regulation in inflammation | Young Jae Kim | Organelle Institute, Kyungpook National University |  | Korea | invivor@gmail.com | 010-4345-4864
|  |  | 11:00-11:20 |  | 20' | Break
|  | Tamna Hall A | 11:20-12:20 | 11:20-12:20 | 50 | PL 3 | How nature and nurture conspire to control brain development and function | Michael Greenberg | the Nathan Marsh Pusey Professor of Neurobiology at Harvard Medical School | Ph.D. | USA | Michael_Greenberg@hms.harvard.edu
| 1 | Yeongju Hall | 12:20-13:10 (Luncheon symposia) |  | 50 | Luncheon
| 1 | Baekrok Hall |  |  | 50 | Lee Se Yong outstanding Ph.D. thesis award lectures
| 1 | Event hall A |  |  | 50 | Luncheon
| 3 | Halla Hall |  |  | 50 | Luncheon
| 3 | Samda Hall |  |  | 50 | Research ethics sym. *Korean
| 5 | Tamna Hall A |  |  | 50 | Luncheon
|  |  | 13:10-13:30 |  | 20' | Break
| 5 | Tamna Hall A | 13:30-13:50 |  | 20 | KSMCB Wunbong academic award lecture
| 5 | Tamna Hall A | 13:50-14:20 |  | 30 | KSMCB life science award lecture
| 5 | Tamna Hall A | 14:20-14:50 |  | 30' | Closing Ceremony KSMCB M&C award / Hanmi TGA / Excellent poster award / YI research award / Lottery / Closing remarks (Tamna hall A) *Korean

## 기념품 (hidden)
[기념품자료]
구분 | 내용 |  | 제작 소요 기간 | 8월 | [5 empty] | 9일 | [13 empty] | 비고
|  |  |  | 1 | 10 | 15 | 20 | 25 | 30 | 1 D-30 | 9 D-20 | 11 D-18 | 14 D-15 | 16 D-13 | 19 D-10 | 22 D-7 | 23 D-6 | 24 D-5 | 25 D-4 | 26 D-3 | 27 D-2 | 28 D-1 | 29 D-day
VIP | 참가자 기념품 | 자개 명패 | 7일
|  | 코사지 | 3일
일반참가자 | 참가자 기념품 | 가열 텀블러 | 7일
| 기본제공 물품 | 부직포가방 | 5일
|  | 프로그램북 | 5일
|  | 웰컴 쿠키 | 5일
기념품 이미지
VIP |  |  |  |  | 일반참가자 |  |  |  | 기본 제공 물품
자개 명패 |  |  | 코사지 |  | 가열텀블러

## 식음료 (hidden)
[식음료자료]
구분 | 장소/업체명 | 위치 | 거리(icc제주) 도보/차량 | 주차여부 | 메뉴 | 수량 | 비고
웰컴립셉션 | ICC JEJU 5층 오션뷰 | ICC JEJU 5층 |  | 가능 | 퓨전한식
양식
도시락
뷔페
| 델리지아 레스토랑 | ICC JEJU 3층 |  | 가능 | 한식
양식
VIP만찬 | 대기정 | 대포동 1787 | 7분/1분 | 불가능 | 갈치조림
전복돌솥밥
통갈치구이
고등어구이
| 명호마농갈비 | 대포동 1696 | 12분/1분 | 30대 가능 | 마농갈비+ 마농육회+된장찌개
생안창살+ 생갈비+마농커리
VIP점심 | 아셈푸드 | ICC JEJU 1층 |  | 가능 | 파인애플 볶음밥
소고기 쌀국수
푸팟퐁 커리
| 중문해녀의집 | 중문동 2658-2 | 13분/2분 | 10대 가능 | 전복죽
해산물
전복회
참가자점심 | 머먹코 | 대포동 1578-1 | 16분/2분 | 가능 | 집밥정식
갈치조림(2인)
| 도시락업체 | ICC JEJU |  |  | 샌드위치
한식 도시락
양식 도시락